## Project Tracking
PROJECT: Job and Major
STATUS | PRIORITY | DEADLINE | TASK | DESCRIPTION | ASSIGNED TO | % DONE | STATUS KEY | PRIORITY KEY
Document preparation | [6 empty] | Not Started | High
Complete | High | already | task1 | Introduction, Problem, Solution, Project Scopes | Sodaneath and Sreynith | 100% | In Progress | Medium
In Progress | Low | 28/11/2022 | task2 | System Features | Sreynith | 10% | Complete | Low
In Progress | Low | 28/11/2022 | task3 | Technology and Tools | Sodaneath | 10% | On Hold
Overdue
UXUI
In Progress | Medium | 30/11/2022 | task1 | Figma (Design UX-UI) | Sreynith | 90%
API Development
In Progress | Low | 18/12/2022 | task 1 | Android Studio(Front-end) Flutter | Sodaneath | 5%
On Hold | Low |  | task 2 | IntelliJ IDEA (Back-end) Java |  | 0%